## 進歩状況
日付 | 当日の進歩 | 翌日の予定 | 問題点 | 備考
2024-11-06 | ①年末調整データベースの最適化：新たに adjustmentfile テーブルを追加しました。 ②EMSページの進捗：フロントエンドコーディング 40% 完了、バックエンド接続 40% 完了。 | EMSページ：フロントエンドコーディング 80% 目標、バックエンド接続 80% 目標。 | detailfileとresultFileを一つのテーブルにまとめるという考え方が少し理解しづらく、具体的なファイルのアップロード数を把握するのが難しいと思います。新しい adjustmentfile テーブルを作成し、アップロードされたファイルをすべてこのテーブルに統一して管理するのはいかがでしょうか。その方が操作しやすくなると思います。 | 11/07在宅
2024-11-07 | EMSページの進捗： ①フロントエンドコーディング 90% 完了 ②バックエンド接続 60% 完了。 | EMSページ： ①フロントエンドコーディング 100% 目標 ②バックエンド接続 90% 目標。 | データベースのofcfunctionテーブルにadjustment画面の情報を追加しましたが、EMSシステムの画面からアクセスできない問題が発生しています。現時点では解決できていないため、明日出勤している方と一緒に解決できればと思っています。 | 11/08出勤
2024-11-08 | EMSページの進捗： ①フロントエンドコーディング 100% 完了 ②バックエンド接続 80% 完了。 | EMSMページ： ①フロントエンドコーディング 30% 目標 EMSページ： ②バックエンド接続 95% 目標。 | ファイルをサーバーにアップロードする問題はまだ解決していません。
2024-11-11 | EMSページの進捗： アップロード機能 90% 完了。 | EMSMページ： ①フロントエンドコーディング 30% 目標。 EMSページ： ②バックエンド接続 100% 目標。 | アップロード機能は実装済みですが、現在、ファイルをアップロードするとサーバーエラーが発生し、まだ解決できていません。 | 11/12出勤
2024-11-12 | EMSページの進捗： アップロード機能 95% 完了。 | EMSMページ： ①フロントエンドコーディング 30% 目標。 EMSページ： ②バックエンド接続 100% 目標。 | アップロード機能がすでに使えるようになったものの、アップロードしたファイルはまだ年度に分類されておらず、すべて履歴に表示されています。明日この問題を解決する予定です。 | 11/13在宅
2024-11-13 | EMSページの進捗： アップロード機能完了。 | EMSMページ： ①フロントエンドコーディング 50% 目標。 | アップロード機能完了しました。 | 11/14出勤
2024-11-14 | ①EMSページの進捗： バックエンド接続 100% 目標。 ②EMSMページ： フロントエンドコーディング 30%完了。 | EMSMページ： ①フロントエンドコーディング 80% 目標。 ②バックエンド接続 50% 目標。 |  | 11/15出勤

## DB
CREATE TABLE adjustmentdetail (
id INT AUTO_INCREMENT PRIMARY KEY,
year VARCHAR(4) NOT NULL,
employeeEmail VARCHAR(255) NOT NULL,
uploadStatus VARCHAR(50),
adjustmentStatus VARCHAR(50),
insertDate DATETIME,
updateDate DATETIME,
INDEX(year, employeeEmail) -- 可选，提高查询效率
);
INSERT INTO `ofcfunction` (`functionID`, `functionName`, `functionText`, `authority`, `functionLink`, `displayNo`, `sysType`, `deleteFlg`, `insertDate`, `updateDate`)VALUES ('B4', 'Adjustment', '&#xe681;&emsp;年末調整画面', 1, '/adjustment',6, '1', 0, DATE_FORMAT(CURDATE(), '%Y%m%d'), DATE_FORMAT(CURDATE(), '%Y%m%d'));
CREATE TABLE `adjustmentRequest` (
`id` INT AUTO_INCREMENT PRIMARY KEY, -- 使用自增主键
`year` INT NOT NULL,
`employeeEmail` VARCHAR(255) NOT NULL, -- 记录上传的员工邮箱
`insertDate` DATE NOT NULL,
`updateDate` DATE NOT NULL
) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4;
CREATE TABLE `adjustmentrequestFiles` (
`fileID` INT AUTO_INCREMENT PRIMARY KEY, -- 文件的自增主键
`requestID` INT NOT NULL, -- 关联到adjustmentRequest表的ID
`fileName` VARCHAR(255) NOT NULL, -- 文件名
`fileULStatus` VARCHAR(1) NOT NULL, -- 上传状态
`fileInsertDate` DATE NOT NULL, -- 文件的上传日期
`fileUpdateDate` DATE NOT NULL, -- 文件的更新日期
FOREIGN KEY (`requestID`) REFERENCES `adjustmentRequest`(`id`) ON DELETE CASCADE
) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4;
CREATE TABLE `adjustmentfile` (
`fileID` INT AUTO_INCREMENT PRIMARY KEY,
`employeeEmail` VARCHAR(255) NOT NULL,
`fileType` VARCHAR(255) NOT NULL, -- "detail" or "result"
`fileYear` INT NOT NULL,
`fileName` VARCHAR(255) NOT NULL,
`filePath` VARCHAR(255) NOT NULL
) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4;

## web
adjustment.html
<!DOCTYPE html>
<html xmlns:th="http://www.thymeleaf.org">
<head>
<meta charset="UTF-8">
<title>年末調整画面</title>
<style>
.table-container {
width: 50%;
margin-left: 20px;
margin-bottom: 20px;
}
h1 {
text-align: center;
font-size: 24px;
font-weight: bold;
}
table {
width: 100%;
margin-top: 20px;
border-collapse: collapse;
}
th, td {
border: 2px solid #b3cbde;
padding: 15px;
text-align: left;
}
th {
height: 40px;
width: 20%;
}
.upload-area {
margin-bottom: 20px;
}
.file-list {
list-style: none;
padding: 0;
}
.file-item {
margin-bottom: 5px;
}
.file-input {
display: none;
}
.custom-button {
display: inline-block;
padding: 10px 15px;
background-color: #7fa3bc;
color: white;
cursor: pointer;
margin-top: 10px;
}
.delete-btn {
margin-left: 10px;
cursor: pointer;
}
.button-container {
text-align: right;
padding-right: 10px;
padding-top: 10px;
}
.history-header {
width: 10%;
text-align: left;
}
.year-header, .file-name-header {
height: 30px;
}
.year-header {
width: 10%;
text-align: left;
}
.file-name-header {
width: 80%;
text-align: left;
}
.file-name-cell {
height: 50px;
text-align: left;
}
</style>
</head>
<body>
<div class="table-container">
<h1>年末調整</h1>
<table>
<tr>
<th>年度</th>
<td th:text="${currentYear}"></td>
</tr>
<tr>
<th>申請書</th>
<td>
<div th:if="${requestFile1ULStatus == 1}">
<a th:href="@{|/download/${requestFile1Name}|}" th:text="${requestFile1Name}"></a>
</div>
<div th:if="${requestFile2ULStatus == 1}">
<a th:href="@{|/download/${requestFile2Name}|}" th:text="${requestFile2Name}"></a>
</div>
</td>
</tr>
<tr>
<th>アップロード</th>
<td>
<div class="upload-area">
<input type="file" id="fileUpload" multiple class="file-input" onchange="updateFileList()"/>
<label for="fileUpload" class="custom-button">ファイルを選択</label>
<ul id="fileList"></ul>
</div>
</td>
</tr>
</table>
<div class="button-container">
<button onclick="submitFiles()">確定</button>
</div>
<!-- 新增结果表格 -->
<table>
<tr>
<th>結果</th>
<td th:each="file : ${resultFiles}">
<a th:if="${file != null}" th:href="@{|/Users/yangxiwen/Documents/work/${fileYear}/${employeeEmail}/${file.fileName}|}" th:text="${file.fileName}"></a>
</td>
</tr>
</table>
<!-- 履歴表格 -->
<table>
<tr>
<th class="history-header" rowspan="11">履歴</th>
<th class="year-header">年度</th>
<th class="file-name-header">ファイル</th>
</tr>
<tr th:each="entry : ${historiesByYear}">
<td class="year-header" th:text="${entry.key}"></td>
<td class="file-name-cell">
<div th:each="file : ${entry.value}">
<a th:if="${file.fileName != null}"
th:href="@{/download/{fileYear}/{employeeEmail}/{filename}(fileYear=${file.fileYear},employeeEmail=${file.employeeEmail},filename=${file.fileName})}"
th:text="${file.fileName}"></a>
</div>
</td>
</tr>
</table>
</div>
<script>
function updateFileList() {
const input = document.getElementById('fileUpload');
const fileList = document.getElementById('fileList');
fileList.innerHTML = ''; // Clear existing list
Array.from(input.files).forEach((file, index) => {
const li = document.createElement('li');
li.textContent = file.name;
li.classList.add('file-item');
const deleteBtn = document.createElement('button');
deleteBtn.textContent = '削除';
deleteBtn.className = 'delete-btn';
deleteBtn.onclick = function() { this.parentElement.remove(); };
li.appendChild(deleteBtn);
fileList.appendChild(li);
});
}
function submitFiles() {
const files = document.getElementById('fileUpload').files;
if (files.length === 0) {
alert('ファイルを選択してください。');
return;
}
const formData = new FormData();
for (let i = 0; i < files.length; i++) {
formData.append('files', files[i]);
}
fetch('/saveFileAndDetail', {
method: 'POST',
body: formData,
credentials: 'include' // セッション情報を維持
})
.then(response => {
if (response.ok) {
return response.text();
} else {
throw new Error('サーバーで問題が発生しました！');
}
})
.then(data => alert('ファイルのアップロードに成功しました: ' + data))
.catch(error => alert('ファイルのアップロードに失敗しました: ' + error));
}
</script>
</body>
</html>

## Back-end
AdjustmentController.java
AdjustmentService.java
AdjustmentDetail.java
AdjustmentFile.java
AdjustmentRequest.java
AdjustmentDetailMapper.java
AdjustmentFileMapper.java
AdjustmentRequestMapper.java
AdjustmentDetailMapper.xml
AdjustmentFileMapper.xml
AdjustmentRequestMapper.xml
package com.softtech.controller;
import java.io.IOException;
import java.nio.file.Files;
import java.nio.file.Path;
import java.time.LocalDate;
import java.util.List;
import java.util.Map;
import javax.servlet.http.HttpSession;
import org.springframework.beans.factory.annotation.Autowired;
import org.springframework.core.io.Resource;
import org.springframework.core.io.UrlResource;
import org.springframework.http.HttpHeaders;
import org.springframework.http.HttpStatus;
import org.springframework.http.ResponseEntity;
import org.springframework.stereotype.Controller;
import org.springframework.ui.Model;
import org.springframework.web.bind.annotation.GetMapping;
import org.springframework.web.bind.annotation.PathVariable;
import org.springframework.web.bind.annotation.PostMapping;
import org.springframework.web.bind.annotation.RequestParam;
import org.springframework.web.bind.annotation.ResponseBody;
import org.springframework.web.multipart.MultipartFile;
import com.softtech.entity.AdjustmentFile;
import com.softtech.service.AdjustmentService;
@Controller
public class AdjustmentController {
@Autowired
private AdjustmentService adjustmentService;
@GetMapping("/adjustment")
public String showAdjustmentPage(Model model, HttpSession session) {
String employeeEmail = (String) session.getAttribute("userMailAdress");
if (employeeEmail == null) {
return "redirect:/login";
}
int currentYear = LocalDate.now().getYear();
model.addAttribute("currentYear", currentYear);
Map<Integer, List<AdjustmentFile>> historiesByYear = adjustmentService.getHistoricalFilesGroupedByYear(employeeEmail);
model.addAttribute("historiesByYear", historiesByYear);
return "ems/adjustment";
}
@PostMapping("/saveFileAndDetail")
public ResponseEntity<?> handleSaveFileAndDetail(@RequestParam("files") MultipartFile[] files, HttpSession session) {
String employeeEmail = (String) session.getAttribute("userMailAdress");
if (employeeEmail == null) {
return ResponseEntity.status(HttpStatus.FORBIDDEN).body("{\"error\": \"ユーザーがログインしていません\"}");
}
try {
adjustmentService.saveFilesAndDetails(files, employeeEmail, LocalDate.now().getYear(), "detail");
return ResponseEntity.ok("{\"message\": \"ファイルが正常にアップロードされました\"}");
} catch (IOException e) {
return ResponseEntity.status(HttpStatus.INTERNAL_SERVER_ERROR).body("{\"error\": \"ファイルのアップロード中にエラーが発生しました: " + e.getMessage() + "\"}");
}
}
@GetMapping("/download/{fileYear}/{employeeEmail}/{filename}")
@ResponseBody
public ResponseEntity<Resource> downloadFile(
@PathVariable("fileYear") int fileYear,
@PathVariable("employeeEmail") String employeeEmail,
@PathVariable("filename") String filename) {
try {
Path file = adjustmentService.getFilePath(filename, employeeEmail, fileYear);
if (Files.exists(file)) {
Resource resource = new UrlResource(file.toUri());
return ResponseEntity.ok()
.header(HttpHeaders.CONTENT_DISPOSITION, "attachment; filename=\"" + resource.getFilename() + "\"")
.body(resource);
} else {
return ResponseEntity.notFound().build();
}
} catch (Exception e) {
return ResponseEntity.status(HttpStatus.INTERNAL_SERVER_ERROR).build();
}
}
}
package com.softtech.service;
import java.io.IOException;
import java.nio.file.Files;
import java.nio.file.Path;
import java.nio.file.Paths;
import java.nio.file.StandardCopyOption;
import java.util.List;
import java.util.Map;
import java.util.stream.Collectors;
import org.springframework.beans.factory.annotation.Autowired;
import org.springframework.stereotype.Service;
import org.springframework.web.multipart.MultipartFile;
import com.softtech.entity.AdjustmentFile;
import com.softtech.mapper.AdjustmentFileMapper;
@Service
public class AdjustmentService {
@Autowired
private AdjustmentFileMapper adjustmentFileMapper;
public void saveFilesAndDetails(MultipartFile[] files, String employeeEmail, int fileYear, String fileType) throws IOException {
for (MultipartFile file : files) {
if (!file.isEmpty()) {
saveFileAndDetail(file, employeeEmail, fileYear, fileType);
}
}
}
private void saveFileAndDetail(MultipartFile file, String employeeEmail, int fileYear, String fileType) throws IOException {
String originalFileName = file.getOriginalFilename();
Path yearDirectory = Paths.get("/Users/yangxiwen/Documents/work", String.valueOf(fileYear), employeeEmail);
if (!Files.exists(yearDirectory)) {
Files.createDirectories(yearDirectory);
}
Path destinationFile = yearDirectory.resolve(originalFileName);
Files.copy(file.getInputStream(), destinationFile, StandardCopyOption.REPLACE_EXISTING);
AdjustmentFile adjustmentFile = new AdjustmentFile();
adjustmentFile.setEmployeeEmail(employeeEmail);
adjustmentFile.setFileType(fileType);
adjustmentFile.setFileYear(fileYear);
adjustmentFile.setFileName(originalFileName);
adjustmentFile.setFilePath(destinationFile.toString());
adjustmentFileMapper.insert(adjustmentFile);
}
/**
* 指定された従業員のファイルを年度別にグループ化して取得します。
* @param employeeEmail 従業員のメールアドレス
* @return 年度別のファイルリスト
*/
public Map<Integer, List<AdjustmentFile>> getHistoricalFilesGroupedByYear(String employeeEmail) {
List<AdjustmentFile> files = adjustmentFileMapper.findFilesByEmployeeEmail(employeeEmail);
return files.stream().collect(Collectors.groupingBy(AdjustmentFile::getFileYear));
}
public byte[] downloadFile(String filename, String employeeEmail, int fileYear) throws IOException {
Path file = Paths.get("/Users/yangxiwen/Documents/work", String.valueOf(fileYear), employeeEmail, filename);
if (!Files.exists(file)) {
throw new IOException("ファイルが見つかりません: " + file.toString());
}
return Files.readAllBytes(file);
}
public Map<Integer, List<AdjustmentFile>> getHistoricalFilesGroupedByYear(String employeeEmail, int excludeYear) {
List<AdjustmentFile> files = adjustmentFileMapper.findFilesByEmployeeEmail(employeeEmail);
return files.stream()
.filter(file -> file.getFileYear() != excludeYear)
.collect(Collectors.groupingBy(AdjustmentFile::getFileYear));
}
/**
* 根据文件名、员工邮箱和年份获取文件的完整路径。
* @param filename 文件名
* @param employeeEmail 员工邮箱
* @param fileYear 文件所在的年份
* @return 文件的完整路径
*/
public Path getFilePath(String filename, String employeeEmail, int fileYear) {
// 构建文件的存储路径
return Paths.get("/Users/yangxiwen/Documents/work", String.valueOf(fileYear), employeeEmail, filename);
}
}
package com.softtech.entity;
import java.util.Date;
public class AdjustmentDetail {
private Integer id; // 新增字段
private int year;
private String employeeEmail;
private String uploadStatus;
private String adjustmentStatus;
private Date insertDate;
private Date updateDate;
// Getters and Setters
public Integer getId() {
return id;
}
public void setId(Integer id) {
this.id = id;
}
public int getYear() {
return year;
}
public void setYear(int year) {
this.year = year;
}
public String getEmployeeEmail() {
return employeeEmail;
}
public void setEmployeeEmail(String employeeEmail) {
this.employeeEmail = employeeEmail;
}
public String getUploadStatus() {
return uploadStatus;
}
public void setUploadStatus(String uploadStatus) {
this.uploadStatus = uploadStatus;
}
public String getAdjustmentStatus() {
return adjustmentStatus;
}
public void setAdjustmentStatus(String adjustmentStatus) {
this.adjustmentStatus = adjustmentStatus;
}
public Date getInsertDate() {
return insertDate;
}
public void setInsertDate(Date insertDate) {
this.insertDate = insertDate;
}
public Date getUpdateDate() {
return updateDate;
}
public void setUpdateDate(Date updateDate) {
this.updateDate = updateDate;
}
@Override
public String toString() {
return "AdjustmentDetail{" +
"id=" + id +
", year=" + year +
", employeeEmail='" + employeeEmail + '\'' +
", uploadStatus='" + uploadStatus + '\'' +
", adjustmentStatus='" + adjustmentStatus + '\'' +
", insertDate=" + insertDate +
", updateDate=" + updateDate +
'}';
}
}
package com.softtech.entity;
public class AdjustmentFile {
private int fileID;
private String employeeEmail;
private String fileType;
private int fileYear;
private String fileName;
private String filePath;
// Getters and Setters
public int getFileID() {
return fileID;
}
public void setFileID(int fileID) {
this.fileID = fileID;
}
public String getEmployeeEmail() {
return employeeEmail;
}
public void setEmployeeEmail(String employeeEmail) {
this.employeeEmail = employeeEmail;
}
public String getFileType() {
return fileType;
}
public void setFileType(String fileType) {
this.fileType = fileType;
}
public int getFileYear() {
return fileYear;
}
public void setFileYear(int fileYear) {
this.fileYear = fileYear;
}
public String getFileName() {
return fileName;
}
public void setFileName(String fileName) {
this.fileName = fileName;
}
public String getFilePath() {
return filePath;
}
public void setFilePath(String filePath) {
this.filePath = filePath;
}
// 可选的 toString 方法，用于打印对象信息
@Override
public String toString() {
return "AdjustmentFile{" +
"fileID=" + fileID +
", employeeEmail='" + employeeEmail + '\'' +
", fileType='" + fileType + '\'' +
", fileYear=" + fileYear +
", fileName='" + fileName + '\'' +
", filePath='" + filePath + '\'' +
'}';
}
}
package com.softtech.entity;
import java.util.Date;
public class AdjustmentRequest {
private int id;
private int year;
private String employeeEmail;
private String requestFile1ID;
private String requestFile1Name;
private String requestFile1ULStatus;
private String requestFile2ID;
private String requestFile2Name;
private String requestFile2ULStatus;
private Date insertDate;
private Date updateDate;
// Getters and Setters
public int getId() {
return id;
}
public void setId(int id) {
this.id = id;
}
public int getYear() {
return year;
}
public void setYear(int year) {
this.year = year;
}
public String getEmployeeEmail() {
return employeeEmail;
}
public void setEmployeeEmail(String employeeEmail) {
this.employeeEmail = employeeEmail;
}
public String getRequestFile1ID() {
return requestFile1ID;
}
public void setRequestFile1ID(String requestFile1ID) {
this.requestFile1ID = requestFile1ID;
}
public String getRequestFile1Name() {
return requestFile1Name;
}
public void setRequestFile1Name(String requestFile1Name) {
this.requestFile1Name = requestFile1Name;
}
public String getRequestFile1ULStatus() {
return requestFile1ULStatus;
}
public void setRequestFile1ULStatus(String requestFile1ULStatus) {
this.requestFile1ULStatus = requestFile1ULStatus;
}
public String getRequestFile2ID() {
return requestFile2ID;
}
public void setRequestFile2ID(String requestFile2ID) {
this.requestFile2ID = requestFile2ID;
}
public String getRequestFile2Name() {
return requestFile2Name;
}
public void setRequestFile2Name(String requestFile2Name) {
this.requestFile2Name = requestFile2Name;
}
public String getRequestFile2ULStatus() {
return requestFile2ULStatus;
}
public void setRequestFile2ULStatus(String requestFile2ULStatus) {
this.requestFile2ULStatus = requestFile2ULStatus;
}
public Date getInsertDate() {
return insertDate;
}
public void setInsertDate(Date insertDate) {
this.insertDate = insertDate;
}
public Date getUpdateDate() {
return updateDate;
}
public void setUpdateDate(Date updateDate) {
this.updateDate = updateDate;
}
}
package com.softtech.mapper;
import java.util.List;
import org.apache.ibatis.annotations.Mapper;
import com.softtech.entity.AdjustmentDetail;
@Mapper
public interface AdjustmentDetailMapper {
List<AdjustmentDetail> selectAll();
AdjustmentDetail selectById(Integer id); // 修改为根据 id 查询
int insert(AdjustmentDetail adjustmentDetail);
int update(AdjustmentDetail adjustmentDetail);
int deleteById(Integer id); // 修改为根据 id 删除
}
package com.softtech.mapper;
import java.util.List;
import org.apache.ibatis.annotations.Mapper;
import org.apache.ibatis.annotations.Param;
import com.softtech.entity.AdjustmentFile;
@Mapper
public interface AdjustmentFileMapper {
List<AdjustmentFile> selectAll();
AdjustmentFile selectByPrimaryKey(int fileID);
int insert(AdjustmentFile adjustmentFile);
int update(AdjustmentFile adjustmentFile);
int deleteByPrimaryKey(int fileID);
List<AdjustmentFile> findFilesByEmployeeEmail(@Param("employeeEmail") String employeeEmail);
}
<?xml version="1.0" encoding="UTF-8" ?>
<!DOCTYPE mapper
PUBLIC "-//mybatis.org//DTD Mapper 3.0//EN"
"http://mybatis.org/dtd/mybatis-3-mapper.dtd">
<mapper namespace="com.softtech.mapper.AdjustmentDetailMapper">
<!-- Result Mapping -->
<resultMap id="AdjustmentDetailResultMap" type="com.softtech.entity.AdjustmentDetail">
<id property="id" column="id" />
<result property="year" column="year" />
<result property="employeeEmail" column="employeeEmail" />
<result property="uploadStatus" column="uploadStatus" />
<result property="adjustmentStatus" column="adjustmentStatus" />
<result property="insertDate" column="insertDate" />
<result property="updateDate" column="updateDate" />
</resultMap>
<!-- SQL Queries -->
<select id="selectAll" resultMap="AdjustmentDetailResultMap">
SELECT * FROM adjustmentdetail
</select>
<select id="selectById" parameterType="Integer" resultMap="AdjustmentDetailResultMap">
SELECT * FROM adjustmentdetail WHERE id = #{id}
</select>
<insert id="insert" parameterType="com.softtech.entity.AdjustmentDetail">
INSERT INTO adjustmentdetail (year, employeeEmail, uploadStatus, adjustmentStatus, insertDate, updateDate)
VALUES (#{year}, #{employeeEmail}, #{uploadStatus}, #{adjustmentStatus}, #{insertDate}, #{updateDate})
</insert>
<update id="update" parameterType="com.softtech.entity.AdjustmentDetail">
UPDATE adjustmentdetail
SET year = #{year}, employeeEmail = #{employeeEmail}, uploadStatus = #{uploadStatus},
adjustmentStatus = #{adjustmentStatus}, insertDate = #{insertDate}, updateDate = #{updateDate}
WHERE id = #{id}
</update>
<delete id="deleteById" parameterType="Integer">
DELETE FROM adjustmentdetail WHERE id = #{id}
</delete>
</mapper>
<?xml version="1.0" encoding="UTF-8" ?>
<!DOCTYPE mapper
PUBLIC "-//mybatis.org//DTD Mapper 3.0//EN"
"http://mybatis.org/dtd/mybatis-3-mapper.dtd">
<mapper namespace="com.softtech.mapper.AdjustmentFileMapper">
<!-- Result Mapping -->
<resultMap id="AdjustmentFileResultMap" type="com.softtech.entity.AdjustmentFile">
<id property="fileID" column="fileID" />
<result property="employeeEmail" column="employeeEmail" />
<result property="fileType" column="fileType" />
<result property="fileYear" column="fileYear" />
<result property="fileName" column="fileName" />
<result property="filePath" column="filePath" />
</resultMap>
<!-- SQL Queries -->
<select id="selectAll" resultMap="AdjustmentFileResultMap">
SELECT * FROM adjustmentfile
</select>
<select id="selectByPrimaryKey" parameterType="int" resultMap="AdjustmentFileResultMap">
SELECT * FROM adjustmentfile WHERE fileID = #{fileID}
</select>
<insert id="insert" parameterType="com.softtech.entity.AdjustmentFile">
INSERT INTO adjustmentfile (employeeEmail, fileType, fileYear, fileName, filePath)
VALUES (#{employeeEmail}, #{fileType}, #{fileYear}, #{fileName}, #{filePath})
</insert>
<update id="update" parameterType="com.softtech.entity.AdjustmentFile">
UPDATE adjustmentfile
SET employeeEmail = #{employeeEmail}, fileType = #{fileType}, fileYear = #{fileYear},
fileName = #{fileName}, filePath = #{filePath}
WHERE fileID = #{fileID}
</update>
<delete id="deleteByPrimaryKey" parameterType="int">
DELETE FROM adjustmentfile WHERE fileID = #{fileID}
</delete>
<select id="findFilesByEmployeeEmail" parameterType="string" resultMap="AdjustmentFileResultMap">
SELECT * FROM adjustmentfile WHERE employeeEmail = #{employeeEmail}
</select>
</mapper>
package com.softtech.mapper;
import java.util.List;
import org.apache.ibatis.annotations.Mapper;
import com.softtech.entity.AdjustmentRequest;
@Mapper
public interface AdjustmentRequestMapper {
List<AdjustmentRequest> selectAll();
AdjustmentRequest selectByPrimaryKey(int id);
int insert(AdjustmentRequest adjustmentRequest);
int update(AdjustmentRequest adjustmentRequest);
int deleteByPrimaryKey(int id);
}
<?xml version="1.0" encoding="UTF-8" ?>
<!DOCTYPE mapper
PUBLIC "-//mybatis.org//DTD Mapper 3.0//EN"
"http://mybatis.org/dtd/mybatis-3-mapper.dtd">
<mapper namespace="com.softtech.mapper.AdjustmentRequestMapper">
<!-- Result Mapping -->
<resultMap id="AdjustmentRequestResultMap" type="com.softtech.entity.AdjustmentRequest">
<id property="id" column="id" />
<result property="year" column="year" />
<result property="employeeEmail" column="employeeEmail" />
<result property="requestFile1ID" column="requestFile1ID" />
<result property="requestFile1Name" column="requestFile1Name" />
<result property="requestFile1ULStatus" column="requestFile1ULStatus" />
<result property="requestFile2ID" column="requestFile2ID" />
<result property="requestFile2Name" column="requestFile2Name" />
<result property="requestFile2ULStatus" column="requestFile2ULStatus" />
<result property="insertDate" column="insertDate" />
<result property="updateDate" column="updateDate" />
</resultMap>
<!-- SQL Queries -->
<select id="selectAll" resultMap="AdjustmentRequestResultMap">
SELECT * FROM adjustmentRequest
</select>
<select id="selectByPrimaryKey" parameterType="int" resultMap="AdjustmentRequestResultMap">
SELECT * FROM adjustmentRequest WHERE id = #{id}
</select>
<insert id="insert" parameterType="com.softtech.entity.AdjustmentRequest">
INSERT INTO adjustmentRequest (year, employeeEmail, requestFile1ID, requestFile1Name, requestFile1ULStatus,
requestFile2ID, requestFile2Name, requestFile2ULStatus, insertDate, updateDate)
VALUES (#{year}, #{employeeEmail}, #{requestFile1ID}, #{requestFile1Name}, #{requestFile1ULStatus},
#{requestFile2ID}, #{requestFile2Name}, #{requestFile2ULStatus}, #{insertDate}, #{updateDate})
</insert>
<update id="update" parameterType="com.softtech.entity.AdjustmentRequest">
UPDATE adjustmentRequest
SET year = #{year}, employeeEmail = #{employeeEmail}, requestFile1ID = #{requestFile1ID},
requestFile1Name = #{requestFile1Name}, requestFile1ULStatus = #{requestFile1ULStatus},
requestFile2ID = #{requestFile2ID}, requestFile2Name = #{requestFile2Name},
requestFile2ULStatus = #{requestFile2ULStatus}, insertDate = #{insertDate}, updateDate = #{updateDate}
WHERE id = #{id}
</update>
<delete id="deleteByPrimaryKey" parameterType="int">
DELETE FROM adjustmentRequest WHERE id = #{id}
</delete>
</mapper>