## 進歩状況
日付 | 当日の進歩 | 翌日の予定 | 問題点 | 備考
2024-11-06 | ①年末調整データベースの最適化：新たに adjustmentfile テーブルを追加しました。 ②EMSページの進捗：フロントエンドコーディング 40% 完了、バックエンド接続 40% 完了。 | EMSページ：フロントエンドコーディング 80% 目標、バックエンド接続 80% 目標。 | detailfileとresultFileを一つのテーブルにまとめるという考え方が少し理解しづらく、具体的なファイルのアップロード数を把握するのが難しいと思います。新しい adjustmentfile テーブルを作成し、アップロードされたファイルをすべてこのテーブルに統一して管理するのはいかがでしょうか。その方が操作しやすくなると思います。 | 11/07在宅
2024-11-07 | EMSページの進捗： ①フロントエンドコーディング 90% 完了 ②バックエンド接続 60% 完了。 | EMSページ： ①フロントエンドコーディング 100% 目標 ②バックエンド接続 90% 目標。 | データベースのofcfunctionテーブルにadjustment画面の情報を追加しましたが、EMSシステムの画面からアクセスできない問題が発生しています。現時点では解決できていないため、明日出勤している方と一緒に解決できればと思っています。 | 11/08出勤
2024-11-08 | EMSページの進捗： ①フロントエンドコーディング 100% 完了 ②バックエンド接続 80% 完了。 | EMSMページ： ①フロントエンドコーディング 30% 目標 EMSページ： ②バックエンド接続 95% 目標。 | ファイルをサーバーにアップロードする問題はまだ解決していません。
2024-11-11 | EMSページの進捗： アップロード機能 90% 完了。 | EMSMページ： ①フロントエンドコーディング 30% 目標。 EMSページ： ②バックエンド接続 100% 目標。 | アップロード機能は実装済みですが、現在、ファイルをアップロードするとサーバーエラーが発生し、まだ解決できていません。 | 11/12出勤
2024-11-12 | EMSページの進捗： アップロード機能 95% 完了。 | EMSMページ： ①フロントエンドコーディング 30% 目標。 EMSページ： ②バックエンド接続 100% 目標。 | アップロード機能がすでに使えるようになったものの、アップロードしたファイルはまだ年度に分類されておらず、すべて履歴に表示されています。明日この問題を解決する予定です。 | 11/13在宅
2024-11-13 | EMSページの進捗： アップロード機能完了。 | EMSMページ： ①フロントエンドコーディング 50% 目標。 | アップロード機能完了しました。 | 11/14出勤
2024-11-14 | ①EMSページの進捗： バックエンド接続 100% 目標。 ②EMSMページ： フロントエンドコーディング 30%完了。 | EMSMページ： ①フロントエンドコーディング 80% 目標。 ②バックエンド接続 50% 目標。 |  | 11/15出勤
2024-11-15 | EMSMページ： ①フロントエンドコーディング 80%完了。 ②バックエンド接続 30% 完了。 | EMSMページ： ①フロントエンドコーディング 100% 目標。 ②バックエンド接続 80% 目標。
2024-11-18 | EMSMページ： ①フロントエンドコーディング 95%完了。 ②バックエンド接続 50% 完了。 | EMSMページ： ①フロントエンドコーディング 100% 目標。 ②バックエンド接続 80% 目標。 |  | 11/19出勤
2024-11-19 | EMSMページ： ①フロントエンドコーディング 100%完了。 ②バックエンド接続 80% 完了。 | EMSMページ： バックエンド接続 100% 目標。 | アップロード機能は実装済みですが、現在、ファイルをアップロードするとサーバーエラーが発生し、まだ解決できていません。 | 11/20在宅

## DB
INSERT INTO `ofcfunction` (`functionID`, `functionName`, `functionText`, `authority`, `functionLink`, `displayNo`, `sysType`, `deleteFlg`, `insertDate`, `updateDate`)VALUES ('B4', 'Adjustment', '&#xe681;&emsp;年末調整画面', 1, '/adjustment',6, '1', 0, DATE_FORMAT(CURDATE(), '%Y%m%d'), DATE_FORMAT(CURDATE(), '%Y%m%d'));
ALTER TABLE `ofcfunction` MODIFY `functionName` VARCHAR(20);
CREATE TABLE `adjustmentRequest` (
`id` INT AUTO_INCREMENT PRIMARY KEY,
`employeeID` VARCHAR(6) NOT NULL,
`employeeEmail` VARCHAR(255) NOT NULL,
`year` INT NOT NULL,
`insertDate` DATE NOT NULL,
`updateDate` DATE NOT NULL,
FOREIGN KEY (`employeeID`) REFERENCES `employee`(`employeeID`) ON DELETE CASCADE
) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4;
CREATE TABLE adjustmentRequestFiles (
fileID INT AUTO_INCREMENT PRIMARY KEY,
requestID INT NOT NULL,
fileName VARCHAR(255) NOT NULL,
fileULStatus VARCHAR(1) NOT NULL,
fileInsertDate DATE NOT NULL,
fileUpdateDate DATE NOT NULL,
FOREIGN KEY (requestID) REFERENCES adjustmentRequest(id) ON DELETE CASCADE
) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4;
CREATE TABLE `adjustmentDetail` (
`id` INT AUTO_INCREMENT PRIMARY KEY,
`employeeID` VARCHAR(6) NOT NULL,
`employeeEmail` VARCHAR(255) NOT NULL,
`year` VARCHAR(4) NOT NULL,
`uploadStatus` VARCHAR(50),
`adjustmentStatus` VARCHAR(50),
`insertDate` DATETIME,
`updateDate` DATETIME,
FOREIGN KEY (`employeeID`) REFERENCES `employee`(`employeeID`) ON DELETE CASCADE,
INDEX(`year`, `employeeID`, `employeeEmail`)
) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4;
CREATE TABLE `adjustmentFile` (
`fileID` INT AUTO_INCREMENT PRIMARY KEY,
`detailID` INT NOT NULL,
`employeeID` VARCHAR(6) NOT NULL,
`employeeEmail` VARCHAR(255) NOT NULL,
`fileType` VARCHAR(255) NOT NULL,
`fileYear` INT NOT NULL,
`fileName` VARCHAR(255) NOT NULL,
`filePath` VARCHAR(255) NOT NULL,
FOREIGN KEY (`employeeID`) REFERENCES `employee`(`employeeID`) ON DELETE CASCADE,
FOREIGN KEY (`detailID`) REFERENCES `adjustmentDetail`(`id`) ON DELETE CASCADE
) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4;

## web
adjustment.html
adjustmentList.jsp
<!DOCTYPE html>
<html xmlns:th="http://www.thymeleaf.org">
<head>
<meta charset="UTF-8">
<title>年末調整画面</title>
<style>
.table-container {
width: 50%;
margin-left: 20px;
margin-bottom: 20px;
}
h1 {
text-align: center;
font-size: 24px;
font-weight: bold;
}
table {
width: 100%;
margin-top: 20px;
border-collapse: collapse;
}
th, td {
border: 2px solid #b3cbde;
padding: 15px;
text-align: left;
}
th {
height: 40px;
width: 20%;
}
.upload-area {
margin-bottom: 20px;
}
.file-list {
list-style: none;
padding: 0;
}
.file-item {
margin-bottom: 5px;
}
.file-input {
display: none;
}
.custom-button {
display: inline-block;
padding: 10px 15px;
background-color: #7fa3bc;
color: white;
cursor: pointer;
margin-top: 10px;
}
.delete-btn {
margin-left: 10px;
cursor: pointer;
}
.button-container {
text-align: right;
padding-right: 10px;
padding-top: 10px;
}
.history-header {
width: 10%;
text-align: left;
}
.year-header, .file-name-header {
height: 30px;
}
.year-header {
width: 10%;
text-align: left;
}
.file-name-header {
width: 80%;
text-align: left;
}
.file-name-cell {
height: 50px;
text-align: left;
}
</style>
</head>
<body>
<div class="table-container">
<h1>年末調整</h1>
<table>
<tr>
<th>年度</th>
<td th:text="${currentYear}"></td>
</tr>
<tr>
<th>申請書</th>
<td>
<div th:if="${requestFile1ULStatus == 1}">
<a th:href="@{/download/{filename}(filename=${requestFile1Name})}" th:text="${requestFile1Name}"></a>
</div>
<div th:if="${requestFile2ULStatus == 1}">
<a th:href="@{/download/{filename}(filename=${requestFile2Name})}" th:text="${requestFile2Name}"></a>
</div>
</td>
</tr>
<tr>
<th>アップロード</th>
<td>
<div class="upload-area">
<input type="file" id="fileUpload" multiple class="file-input" onchange="updateFileList()"/>
<label for="fileUpload" class="custom-button">ファイルを選択</label>
<ul id="fileList"></ul>
</div>
</td>
</tr>
</table>
<div class="button-container">
<button onclick="submitFiles()">確定</button>
</div>
<!-- 新增结果表格 -->
<table>
<tr>
<th>結果</th>
<td th:each="file : ${resultFiles}">
<a th:if="${file != null}" th:href="@{|/Users/yangxiwen/Documents/work/${fileYear}/${employeeEmail}/${file.fileName}|}" th:text="${file.fileName}"></a>
</td>
</tr>
</table>
<!-- 履歴表格 -->
<table>
<tr>
<th class="history-header" rowspan="11">履歴</th>
<th class="year-header">年度</th>
<th class="file-name-header">ファイル</th>
</tr>
<tr th:each="entry : ${historiesByYear}">
<td class="year-header" th:text="${entry.key}"></td>
<td class="file-name-cell">
<div th:each="file : ${entry.value}">
<a th:if="${file.fileName != null}"
th:href="@{/download/{fileYear}/{employeeEmail}/{filename}(fileYear=${file.fileYear},employeeEmail=${file.employeeEmail},filename=${file.fileName})}"
th:text="${file.fileName}"></a>
</div>
</td>
</tr>
</table>
</div>
<script>
function updateFileList() {
const input = document.getElementById('fileUpload');
const fileList = document.getElementById('fileList');
fileList.innerHTML = ''; // Clear existing list
Array.from(input.files).forEach((file, index) => {
const li = document.createElement('li');
li.textContent = file.name;
li.classList.add('file-item');
const deleteBtn = document.createElement('button');
deleteBtn.textContent = '削除';
deleteBtn.className = 'delete-btn';
deleteBtn.onclick = function() { this.parentElement.remove(); };
li.appendChild(deleteBtn);
fileList.appendChild(li);
});
}
function submitFiles() {
const files = document.getElementById('fileUpload').files;
if (files.length === 0) {
alert('ファイルを選択してください。');
return;
}
const formData = new FormData();
for (let i = 0; i < files.length; i++) {
formData.append('files', files[i]);
}
fetch('/saveFileAndDetail', {
method: 'POST',
body: formData,
credentials: 'include' // セッション情報を維持
})
.then(response => {
if (response.ok) {
return response.text();
} else {
throw new Error('サーバーで問題が発生しました！');
}
})
.then(data => alert('ファイルのアップロードに成功しました: ' + data))
.catch(error => alert('ファイルのアップロードに失敗しました: ' + error));
}
</script>
</body>
</html>
<%@ page language="java" contentType="text/html; charset=UTF-8" pageEncoding="UTF-8"%>
<!DOCTYPE html>
<html>
<head>
<meta charset="UTF-8">
<title>年末調整</title>
<style>
.table-container {
width: 50%;
margin-left: 20px;
margin-bottom: 20px;
}
h1 {
text-align: center;
font-size: 24px;
font-weight: bold;
}
table {
width: 100%;
margin-top: 20px;
border-collapse: collapse;
}
th, td {
border: 2px solid #b3cbde;
padding: 15px;
text-align: left;
}
th {
height: 40px;
width: 20%;
}
.upload-area {
display: flex;
justify-content: space-between; /* 确保按钮在同一行并对齐到右侧 */
align-items: center;
margin-bottom: 20px;
}
.file-list {
list-style: none;
padding: 0;
margin-top: 10px;
}
.file-item {
margin-bottom: 5px;
}
.file-input {
display: none;
}
.custom-button {
display: inline-block;
padding: 10px 15px;
background-color: #7fa3bc;
color: white;
cursor: pointer;
}
.delete-btn {
margin-left: 10px;
cursor: pointer;
}
</style>
</head>
<body>
<div class="table-container">
<h1>年末調整</h1>
<table>
<tr>
<th>年度</th>
<td><%= java.time.LocalDate.now().getYear() %></td>
</tr>
<tr>
<th>アップロード</th>
<td>
<div class="upload-area">
<label for="fileUpload" class="custom-button">ファイルを選択</label>
<input type="file" id="fileUpload" multiple class="file-input" onchange="updateFileList()"/>
<button onclick="submitFiles()" class="custom-button">確定</button>
</div>
<ul id="fileList" class="file-list"></ul>
</td>
</tr>
<tr>
<th>申請書</th>
<td id="requestFiles"></td>
</tr>
</table>
<!-- 社員リスト表 -->
<table>
<thead>
<tr>
<th colspan="2" style="text-align: center;">社員リスト</th>
</tr>
<tr>
<th>社員名</th>
<th>調整状況</th>
</tr>
</thead>
<tbody id="employeeList">
<%-- Employee list will be fetched and displayed by JavaScript --%>
</tbody>
</table>
</div>
<script>
document.addEventListener("DOMContentLoaded", function() {
fetch("/getAdjustmentData")
.then(response => response.json())
.then(data => {
const requestFiles = data.requestFiles;
const requestFilesContainer = document.getElementById("requestFiles");
requestFiles.forEach(file => {
const link = document.createElement("a");
link.href = "/download/" + file.fileName;
link.textContent = file.fileName;
requestFilesContainer.appendChild(link);
requestFilesContainer.appendChild(document.createElement("br"));
});
const employeeList = document.getElementById("employeeList");
data.employees.forEach(employee => {
const tr = document.createElement("tr");
const nameTd = document.createElement("td");
const statusTd = document.createElement("td");
nameTd.textContent = employee.employeeName;
statusTd.textContent = employee.adjustmentStatus === "0" ? "調整中" : "調整済み";
tr.appendChild(nameTd);
tr.appendChild(statusTd);
employeeList.appendChild(tr);
});
})
.catch(error => console.error("Error loading data:", error));
});
function updateFileList() {
const input = document.getElementById('fileUpload');
const fileList = document.getElementById('fileList');
fileList.innerHTML = '';
Array.from(input.files).forEach((file, index) => {
const li = document.createElement('li');
li.textContent = file.name;
li.classList.add('file-item');
const deleteBtn = document.createElement('button');
deleteBtn.textContent = '削除';
deleteBtn.className = 'delete-btn';
deleteBtn.onclick = function() { this.parentElement.remove(); };
li.appendChild(deleteBtn);
fileList.appendChild(li);
});
}
function submitFiles() {
const files = document.getElementById('fileUpload').files;
if (files.length === 0) {
alert('ファイルを選択してください。');
return;
}
const formData = new FormData();
for (let i = 0; i < files.length; i++) {
formData.append('files', files[i]);
}
fetch('/uploadFile', {
method: 'POST',
body: formData
})
.then(response => response.json())
.then(data => {
alert(data.message);
location.reload(); // Reload to update the file list
})
.catch(error => {
console.error('Error:', error);
alert('ファイルのアップロードに失敗しました');
});
}
</script>
</body>
</html>

## Back-end
AdjustmentController.java
AdjustmentService.java
AdjustmentDetail.java
AdjustmentFile.java
AdjustmentRequest.java
AdjustmentDetailMapper.java
AdjustmentFileMapper.java
AdjustmentRequestMapper.java
AdjustmentDetailMapper.xml
AdjustmentFileMapper.xml
AdjustmentRequestMapper.xml
package com.softtech.controller;
import java.io.IOException;
import java.nio.file.Files;
import java.nio.file.Path;
import java.time.LocalDate;
import java.util.List;
import java.util.Map;
import javax.servlet.http.HttpSession;
import org.springframework.beans.factory.annotation.Autowired;
import org.springframework.core.io.Resource;
import org.springframework.core.io.UrlResource;
import org.springframework.http.HttpHeaders;
import org.springframework.http.HttpStatus;
import org.springframework.http.ResponseEntity;
import org.springframework.stereotype.Controller;
import org.springframework.ui.Model;
import org.springframework.web.bind.annotation.GetMapping;
import org.springframework.web.bind.annotation.PathVariable;
import org.springframework.web.bind.annotation.PostMapping;
import org.springframework.web.bind.annotation.RequestParam;
import org.springframework.web.bind.annotation.ResponseBody;
import org.springframework.web.multipart.MultipartFile;
import com.softtech.entity.AdjustmentFile;
import com.softtech.service.AdjustmentService;
@Controller
public class AdjustmentController {
@Autowired
private AdjustmentService adjustmentService;
@GetMapping("/adjustment")
public String showAdjustmentPage(Model model, HttpSession session) {
String employeeEmail = (String) session.getAttribute("userMailAdress");
if (employeeEmail == null) {
return "redirect:/login";
}
int currentYear = LocalDate.now().getYear();
model.addAttribute("currentYear", currentYear);
Map<Integer, List<AdjustmentFile>> historiesByYear = adjustmentService.getHistoricalFilesGroupedByYear(employeeEmail);
model.addAttribute("historiesByYear", historiesByYear);
return "ems/adjustment";
}
@PostMapping("/saveFileAndDetail")
public ResponseEntity<?> handleSaveFileAndDetail(@RequestParam("files") MultipartFile[] files, HttpSession session) {
String employeeEmail = (String) session.getAttribute("userEmail");
if (employeeEmail == null) {
return ResponseEntity.status(HttpStatus.FORBIDDEN).body("{\"error\": \"User is not logged in\"}");
}
try {
adjustmentService.saveFilesAndDetails(files, employeeEmail, LocalDate.now().getYear(), "detail");
return ResponseEntity.ok("{\"message\": \"File uploaded successfully\"}");
} catch (IOException e) {
return ResponseEntity.status(HttpStatus.INTERNAL_SERVER_ERROR).body("{\"error\": \"Error uploading file: " + e.getMessage() + "\"}");
}
}
@GetMapping("/download/{fileYear}/{employeeEmail}/{filename}")
@ResponseBody
public ResponseEntity<Resource> downloadFile(
@PathVariable("fileYear") int fileYear,
@PathVariable("employeeEmail") String employeeEmail,
@PathVariable("filename") String filename) {
try {
Path file = adjustmentService.getFilePath(filename, employeeEmail, fileYear);
if (Files.exists(file)) {
Resource resource = new UrlResource(file.toUri());
return ResponseEntity.ok()
.header(HttpHeaders.CONTENT_DISPOSITION, "attachment; filename=\"" + resource.getFilename() + "\"")
.body(resource);
} else {
return ResponseEntity.notFound().build();
}
} catch (Exception e) {
return ResponseEntity.status(HttpStatus.INTERNAL_SERVER_ERROR).build();
}
}
}
package com.softtech.service;
import java.io.IOException;
import java.nio.file.Files;
import java.nio.file.Path;
import java.nio.file.Paths;
import java.nio.file.StandardCopyOption;
import java.util.List;
import java.util.Map;
import java.util.stream.Collectors;
import org.springframework.beans.factory.annotation.Autowired;
import org.springframework.stereotype.Service;
import org.springframework.web.multipart.MultipartFile;
import com.softtech.entity.AdjustmentFile;
import com.softtech.mapper.AdjustmentFileMapper;
@Service
public class AdjustmentService {
@Autowired
private AdjustmentFileMapper adjustmentFileMapper;
public void saveFilesAndDetails(MultipartFile[] files, String employeeEmail, int fileYear, String fileType) throws IOException {
for (MultipartFile file : files) {
if (!file.isEmpty()) {
saveFileAndDetail(file, employeeEmail, fileYear, fileType);
}
}
}
private void saveFileAndDetail(MultipartFile file, String employeeEmail, int fileYear, String fileType) throws IOException {
String originalFileName = file.getOriginalFilename();
Path yearDirectory = Paths.get("/Users/yangxiwen/Documents/work", String.valueOf(fileYear), employeeEmail);
if (!Files.exists(yearDirectory)) {
Files.createDirectories(yearDirectory);
}
Path destinationFile = yearDirectory.resolve(originalFileName);
Files.copy(file.getInputStream(), destinationFile, StandardCopyOption.REPLACE_EXISTING);
AdjustmentFile adjustmentFile = new AdjustmentFile();
adjustmentFile.setEmployeeEmail(employeeEmail);
adjustmentFile.setFileType(fileType);
adjustmentFile.setFileYear(fileYear);
adjustmentFile.setFileName(originalFileName);
adjustmentFile.setFilePath(destinationFile.toString());
adjustmentFileMapper.insert(adjustmentFile);
}
/**
* 指定された従業員のファイルを年度別にグループ化して取得します。
* @param employeeEmail 従業員のメールアドレス
* @return 年度別のファイルリスト
*/
public Map<Integer, List<AdjustmentFile>> getHistoricalFilesGroupedByYear(String employeeEmail) {
List<AdjustmentFile> files = adjustmentFileMapper.findFilesByEmployeeEmail(employeeEmail);
return files.stream().collect(Collectors.groupingBy(AdjustmentFile::getFileYear));
}
public byte[] downloadFile(String filename, String employeeEmail, int fileYear) throws IOException {
Path file = Paths.get("/Users/yangxiwen/Documents/work", String.valueOf(fileYear), employeeEmail, filename);
if (!Files.exists(file)) {
throw new IOException("ファイルが見つかりません: " + file.toString());
}
return Files.readAllBytes(file);
}
public Map<Integer, List<AdjustmentFile>> getHistoricalFilesGroupedByYear(String employeeEmail, int excludeYear) {
List<AdjustmentFile> files = adjustmentFileMapper.findFilesByEmployeeEmail(employeeEmail);
return files.stream()
.filter(file -> file.getFileYear() != excludeYear)
.collect(Collectors.groupingBy(AdjustmentFile::getFileYear));
}
/**
* 根据文件名、员工邮箱和年份获取文件的完整路径。
* @param filename 文件名
* @param employeeEmail 员工邮箱
* @param fileYear 文件所在的年份
* @return 文件的完整路径
*/
public Path getFilePath(String filename, String employeeEmail, int fileYear) {
// 构建文件的存储路径
return Paths.get("/Users/yangxiwen/Documents/work", String.valueOf(fileYear), employeeEmail, filename);
}
}
package com.softtech.entity;
import java.util.Date;
public class AdjustmentDetail {
private Integer id; // 新增字段
private int year;
private String employeeEmail;
private String uploadStatus;
private String adjustmentStatus;
private Date insertDate;
private Date updateDate;
// Getters and Setters
public Integer getId() {
return id;
}
public void setId(Integer id) {
this.id = id;
}
public int getYear() {
return year;
}
public void setYear(int year) {
this.year = year;
}
public String getEmployeeEmail() {
return employeeEmail;
}
public void setEmployeeEmail(String employeeEmail) {
this.employeeEmail = employeeEmail;
}
public String getUploadStatus() {
return uploadStatus;
}
public void setUploadStatus(String uploadStatus) {
this.uploadStatus = uploadStatus;
}
public String getAdjustmentStatus() {
return adjustmentStatus;
}
public void setAdjustmentStatus(String adjustmentStatus) {
this.adjustmentStatus = adjustmentStatus;
}
public Date getInsertDate() {
return insertDate;
}
public void setInsertDate(Date insertDate) {
this.insertDate = insertDate;
}
public Date getUpdateDate() {
return updateDate;
}
public void setUpdateDate(Date updateDate) {
this.updateDate = updateDate;
}
@Override
public String toString() {
return "AdjustmentDetail{" +
"id=" + id +
", year=" + year +
", employeeEmail='" + employeeEmail + '\'' +
", uploadStatus='" + uploadStatus + '\'' +
", adjustmentStatus='" + adjustmentStatus + '\'' +
", insertDate=" + insertDate +
", updateDate=" + updateDate +
'}';
}
}
package com.softtech.entity;
public class AdjustmentFile {
private int fileID;
private String employeeEmail;
private String fileType;
private int fileYear;
private String fileName;
private String filePath;
// Getters and Setters
public int getFileID() {
return fileID;
}
public void setFileID(int fileID) {
this.fileID = fileID;
}
public String getEmployeeEmail() {
return employeeEmail;
}
public void setEmployeeEmail(String employeeEmail) {
this.employeeEmail = employeeEmail;
}
public String getFileType() {
return fileType;
}
public void setFileType(String fileType) {
this.fileType = fileType;
}
public int getFileYear() {
return fileYear;
}
public void setFileYear(int fileYear) {
this.fileYear = fileYear;
}
public String getFileName() {
return fileName;
}
public void setFileName(String fileName) {
this.fileName = fileName;
}
public String getFilePath() {
return filePath;
}
public void setFilePath(String filePath) {
this.filePath = filePath;
}
// 可选的 toString 方法，用于打印对象信息
@Override
public String toString() {
return "AdjustmentFile{" +
"fileID=" + fileID +
", employeeEmail='" + employeeEmail + '\'' +
", fileType='" + fileType + '\'' +
", fileYear=" + fileYear +
", fileName='" + fileName + '\'' +
", filePath='" + filePath + '\'' +
'}';
}
}
package com.softtech.entity;
import java.util.Date;
public class AdjustmentRequest {
private int id;
private int year;
private String employeeEmail;
private String requestFile1ID;
private String requestFile1Name;
private String requestFile1ULStatus;
private String requestFile2ID;
private String requestFile2Name;
private String requestFile2ULStatus;
private Date insertDate;
private Date updateDate;
// Getters and Setters
public int getId() {
return id;
}
public void setId(int id) {
this.id = id;
}
public int getYear() {
return year;
}
public void setYear(int year) {
this.year = year;
}
public String getEmployeeEmail() {
return employeeEmail;
}
public void setEmployeeEmail(String employeeEmail) {
this.employeeEmail = employeeEmail;
}
public String getRequestFile1ID() {
return requestFile1ID;
}
public void setRequestFile1ID(String requestFile1ID) {
this.requestFile1ID = requestFile1ID;
}
public String getRequestFile1Name() {
return requestFile1Name;
}
public void setRequestFile1Name(String requestFile1Name) {
this.requestFile1Name = requestFile1Name;
}
public String getRequestFile1ULStatus() {
return requestFile1ULStatus;
}
public void setRequestFile1ULStatus(String requestFile1ULStatus) {
this.requestFile1ULStatus = requestFile1ULStatus;
}
public String getRequestFile2ID() {
return requestFile2ID;
}
public void setRequestFile2ID(String requestFile2ID) {
this.requestFile2ID = requestFile2ID;
}
public String getRequestFile2Name() {
return requestFile2Name;
}
public void setRequestFile2Name(String requestFile2Name) {
this.requestFile2Name = requestFile2Name;
}
public String getRequestFile2ULStatus() {
return requestFile2ULStatus;
}
public void setRequestFile2ULStatus(String requestFile2ULStatus) {
this.requestFile2ULStatus = requestFile2ULStatus;
}
public Date getInsertDate() {
return insertDate;
}
public void setInsertDate(Date insertDate) {
this.insertDate = insertDate;
}
public Date getUpdateDate() {
return updateDate;
}
public void setUpdateDate(Date updateDate) {
this.updateDate = updateDate;
}
}
package com.softtech.mapper;
import java.util.List;
import org.apache.ibatis.annotations.Mapper;
import com.softtech.entity.AdjustmentDetail;
@Mapper
public interface AdjustmentDetailMapper {
List<AdjustmentDetail> selectAll();
AdjustmentDetail selectById(Integer id); // 修改为根据 id 查询
int insert(AdjustmentDetail adjustmentDetail);
int update(AdjustmentDetail adjustmentDetail);
int deleteById(Integer id); // 修改为根据 id 删除
}
package com.softtech.mapper;
import java.util.List;
import org.apache.ibatis.annotations.Mapper;
import org.apache.ibatis.annotations.Param;
import com.softtech.entity.AdjustmentFile;
@Mapper
public interface AdjustmentFileMapper {
List<AdjustmentFile> selectAll();
AdjustmentFile selectByPrimaryKey(int fileID);
int insert(AdjustmentFile adjustmentFile);
int update(AdjustmentFile adjustmentFile);
int deleteByPrimaryKey(int fileID);
List<AdjustmentFile> findFilesByEmployeeEmail(@Param("employeeEmail") String employeeEmail);
}
<?xml version="1.0" encoding="UTF-8" ?>
<!DOCTYPE mapper
PUBLIC "-//mybatis.org//DTD Mapper 3.0//EN"
"http://mybatis.org/dtd/mybatis-3-mapper.dtd">
<mapper namespace="com.softtech.mapper.AdjustmentDetailMapper">
<!-- Result Mapping -->
<resultMap id="AdjustmentDetailResultMap" type="com.softtech.entity.AdjustmentDetail">
<id property="id" column="id" />
<result property="year" column="year" />
<result property="employeeEmail" column="employeeEmail" />
<result property="uploadStatus" column="uploadStatus" />
<result property="adjustmentStatus" column="adjustmentStatus" />
<result property="insertDate" column="insertDate" />
<result property="updateDate" column="updateDate" />
</resultMap>
<!-- SQL Queries -->
<select id="selectAll" resultMap="AdjustmentDetailResultMap">
SELECT * FROM adjustmentdetail
</select>
<select id="selectById" parameterType="Integer" resultMap="AdjustmentDetailResultMap">
SELECT * FROM adjustmentdetail WHERE id = #{id}
</select>
<insert id="insert" parameterType="com.softtech.entity.AdjustmentDetail">
INSERT INTO adjustmentdetail (year, employeeEmail, uploadStatus, adjustmentStatus, insertDate, updateDate)
VALUES (#{year}, #{employeeEmail}, #{uploadStatus}, #{adjustmentStatus}, #{insertDate}, #{updateDate})
</insert>
<update id="update" parameterType="com.softtech.entity.AdjustmentDetail">
UPDATE adjustmentdetail
SET year = #{year}, employeeEmail = #{employeeEmail}, uploadStatus = #{uploadStatus},
adjustmentStatus = #{adjustmentStatus}, insertDate = #{insertDate}, updateDate = #{updateDate}
WHERE id = #{id}
</update>
<delete id="deleteById" parameterType="Integer">
DELETE FROM adjustmentdetail WHERE id = #{id}
</delete>
</mapper>
<?xml version="1.0" encoding="UTF-8" ?>
<!DOCTYPE mapper
PUBLIC "-//mybatis.org//DTD Mapper 3.0//EN"
"http://mybatis.org/dtd/mybatis-3-mapper.dtd">
<mapper namespace="com.softtech.mapper.AdjustmentFileMapper">
<!-- Result Mapping -->
<resultMap id="AdjustmentFileResultMap" type="com.softtech.entity.AdjustmentFile">
<id property="fileID" column="fileID" />
<result property="employeeEmail" column="employeeEmail" />
<result property="fileType" column="fileType" />
<result property="fileYear" column="fileYear" />
<result property="fileName" column="fileName" />
<result property="filePath" column="filePath" />
</resultMap>
<!-- SQL Queries -->
<select id="selectAll" resultMap="AdjustmentFileResultMap">
SELECT * FROM adjustmentfile
</select>
<select id="selectByPrimaryKey" parameterType="int" resultMap="AdjustmentFileResultMap">
SELECT * FROM adjustmentfile WHERE fileID = #{fileID}
</select>
<insert id="insert" parameterType="com.softtech.entity.AdjustmentFile">
INSERT INTO adjustmentfile (employeeEmail, fileType, fileYear, fileName, filePath)
VALUES (#{employeeEmail}, #{fileType}, #{fileYear}, #{fileName}, #{filePath})
</insert>
<update id="update" parameterType="com.softtech.entity.AdjustmentFile">
UPDATE adjustmentfile
SET employeeEmail = #{employeeEmail}, fileType = #{fileType}, fileYear = #{fileYear},
fileName = #{fileName}, filePath = #{filePath}
WHERE fileID = #{fileID}
</update>
<delete id="deleteByPrimaryKey" parameterType="int">
DELETE FROM adjustmentfile WHERE fileID = #{fileID}
</delete>
<select id="findFilesByEmployeeEmail" parameterType="string" resultMap="AdjustmentFileResultMap">
SELECT * FROM adjustmentfile WHERE employeeEmail = #{employeeEmail}
</select>
</mapper>
package com.softtech.mapper;
import java.util.List;
import org.apache.ibatis.annotations.Mapper;
import com.softtech.entity.AdjustmentRequest;
@Mapper
public interface AdjustmentRequestMapper {
List<AdjustmentRequest> selectAll();
AdjustmentRequest selectByPrimaryKey(int id);
int insert(AdjustmentRequest adjustmentRequest);
int update(AdjustmentRequest adjustmentRequest);
int deleteByPrimaryKey(int id);
}
<?xml version="1.0" encoding="UTF-8" ?>
<!DOCTYPE mapper
PUBLIC "-//mybatis.org//DTD Mapper 3.0//EN"
"http://mybatis.org/dtd/mybatis-3-mapper.dtd">
<mapper namespace="com.softtech.mapper.AdjustmentRequestMapper">
<!-- Result Mapping -->
<resultMap id="AdjustmentRequestResultMap" type="com.softtech.entity.AdjustmentRequest">
<id property="id" column="id" />
<result property="year" column="year" />
<result property="employeeEmail" column="employeeEmail" />
<result property="requestFile1ID" column="requestFile1ID" />
<result property="requestFile1Name" column="requestFile1Name" />
<result property="requestFile1ULStatus" column="requestFile1ULStatus" />
<result property="requestFile2ID" column="requestFile2ID" />
<result property="requestFile2Name" column="requestFile2Name" />
<result property="requestFile2ULStatus" column="requestFile2ULStatus" />
<result property="insertDate" column="insertDate" />
<result property="updateDate" column="updateDate" />
</resultMap>
<!-- SQL Queries -->
<select id="selectAll" resultMap="AdjustmentRequestResultMap">
SELECT * FROM adjustmentRequest
</select>
<select id="selectByPrimaryKey" parameterType="int" resultMap="AdjustmentRequestResultMap">
SELECT * FROM adjustmentRequest WHERE id = #{id}
</select>
<insert id="insert" parameterType="com.softtech.entity.AdjustmentRequest">
INSERT INTO adjustmentRequest (year, employeeEmail, requestFile1ID, requestFile1Name, requestFile1ULStatus,
requestFile2ID, requestFile2Name, requestFile2ULStatus, insertDate, updateDate)
VALUES (#{year}, #{employeeEmail}, #{requestFile1ID}, #{requestFile1Name}, #{requestFile1ULStatus},
#{requestFile2ID}, #{requestFile2Name}, #{requestFile2ULStatus}, #{insertDate}, #{updateDate})
</insert>
<update id="update" parameterType="com.softtech.entity.AdjustmentRequest">
UPDATE adjustmentRequest
SET year = #{year}, employeeEmail = #{employeeEmail}, requestFile1ID = #{requestFile1ID},
requestFile1Name = #{requestFile1Name}, requestFile1ULStatus = #{requestFile1ULStatus},
requestFile2ID = #{requestFile2ID}, requestFile2Name = #{requestFile2Name},
requestFile2ULStatus = #{requestFile2ULStatus}, insertDate = #{insertDate}, updateDate = #{updateDate}
WHERE id = #{id}
</update>
<delete id="deleteByPrimaryKey" parameterType="int">
DELETE FROM adjustmentRequest WHERE id = #{id}
</delete>
</mapper>