## 進歩状況
日付 | 当日の進歩 | 翌日の予定 | 問題点 | 備考
2024-11-06 | ①年末調整データベースの最適化：新たに adjustmentfile テーブルを追加しました。 ②EMSページの進捗：フロントエンドコーディング 40% 完了、バックエンド接続 40% 完了。 | EMSページ：フロントエンドコーディング 80% 目標、バックエンド接続 80% 目標。 | detailfileとresultFileを一つのテーブルにまとめるという考え方が少し理解しづらく、具体的なファイルのアップロード数を把握するのが難しいと思います。新しい adjustmentfile テーブルを作成し、アップロードされたファイルをすべてこのテーブルに統一して管理するのはいかがでしょうか。その方が操作しやすくなると思います。 | 11/07在宅
2024-11-07 | EMSページの進捗： ①フロントエンドコーディング 90% 完了 ②バックエンド接続 60% 完了。 | EMSページ： ①フロントエンドコーディング 100% 目標 ②バックエンド接続 90% 目標。 | データベースのofcfunctionテーブルにadjustment画面の情報を追加しましたが、EMSシステムの画面からアクセスできない問題が発生しています。現時点では解決できていないため、明日出勤している方と一緒に解決できればと思っています。 | 11/08出勤
2024-11-08 | EMSページの進捗： ①フロントエンドコーディング 100% 完了 ②バックエンド接続 80% 完了。 | EMSMページ： ①フロントエンドコーディング 30% 目標 ②バックエンド接続 95% 目標。 | ファイルをサーバーにアップロードする問題はまだ解決していません。

## DB
CREATE TABLE `adjustmentdetail` (
`year` INT NOT NULL,
`employeeID` VARCHAR(6) NOT NULL,
`uploadStatus` VARCHAR(2) NOT NULL,
`adjustmentStatus` VARCHAR(2) NOT NULL,
`insertDate` DATE NOT NULL,
`updateDate` DATE NOT NULL,
PRIMARY KEY (`year`, `employeeID`),
FOREIGN KEY (`employeeID`) REFERENCES `employee` (`employeeID`) ON DELETE CASCADE ON UPDATE CASCADE
) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4;
CREATE TABLE `adjustmentRequest` (
`year` INT NOT NULL,
`employeeID` VARCHAR(6) NOT NULL,
`requestFile1ID` VARCHAR(2),
`requestFile1Name` VARCHAR(255),
`requestFile1ULStatus` VARCHAR(1),
`requestFile2ID` VARCHAR(2),
`requestFile2Name` VARCHAR(255),
`requestFile2ULStatus` VARCHAR(1),
`insertDate` DATE NOT NULL,
`updateDate` DATE NOT NULL,
PRIMARY KEY (`year`, `employeeID`),
FOREIGN KEY (`employeeID`) REFERENCES `employee` (`employeeID`) ON DELETE CASCADE ON UPDATE CASCADE
) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4;
CREATE TABLE `adjustmentfile` (
`fileID` INT AUTO_INCREMENT PRIMARY KEY,
`employeeID` VARCHAR(6) NOT NULL,
`fileType` VARCHAR(255) NOT NULL, -- "detail" or "result"
`fileYear` INT NOT NULL,
`fileName` VARCHAR(255) NOT NULL,
`filePath` VARCHAR(255) NOT NULL,
FOREIGN KEY (`employeeID`) REFERENCES `employee` (`employeeID`) ON DELETE CASCADE ON UPDATE CASCADE
) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4;
INSERT INTO `ofcfunction` (`functionID`, `functionName`, `functionText`, `authority`, `functionLink`, `displayNo`, `sysType`, `deleteFlg`, `insertDate`, `updateDate`)VALUES ('B4', 'Adjustment', '&#xe681;&emsp;年末調整画面', 1, '/adjustment',6, '1', 0, DATE_FORMAT(CURDATE(), '%Y%m%d'), DATE_FORMAT(CURDATE(), '%Y%m%d'));

## web
adjustment.html
<!DOCTYPE html>
<html xmlns:th="http://www.thymeleaf.org">
<head>
<meta charset="UTF-8">
<title>年末調整画面</title>
<style>
.table-container {
width: 50%;
margin-left: 20px;
margin-bottom: 20px;
}
h1 {
text-align: center;
font-size: 24px;
font-weight: bold;
}
table {
width: 100%;
margin-top: 20px;
border-collapse: collapse;
}
th, td {
border: 2px solid #b3cbde;
padding: 15px;
text-align: left;
}
th {
height: 40px;
width: 20%;
}
.upload-area {
margin-bottom: 20px;
}
.file-list {
list-style: none;
padding: 0;
}
.file-item {
margin-bottom: 5px;
}
.file-input {
display: none;
}
.custom-button {
display: inline-block;
padding: 10px 15px;
background-color: #7fa3bc;
color: white;
cursor: pointer;
margin-top: 10px;
}
.delete-btn {
margin-left: 10px;
cursor: pointer;
}
.button-container {
text-align: right;
padding-right: 10px;
padding-top: 10px;
}
.history-header {
width: 10%;
text-align: left;
}
.year-header, .file-name-header {
height: 30px;
}
.year-header {
width: 10%;
text-align: left;
}
.file-name-header {
width: 80%;
text-align: left;
}
.file-name-cell {
height: 50px;
text-align: left;
}
</style>
</head>
<body>
<div class="table-container">
<h1>年末調整</h1>
<table>
<tr>
<th>年度</th>
<td th:text="${currentYear}"></td>
</tr>
<tr>
<th>申請書</th>
<td>
<div th:if="${requstFileI1ULStatus == 1}">
<a th:href="@{|/download/${requstFile1Name}|}" th:text="${requstFile1Name}"></a>
</div>
<div th:if="${requstFileI2ULStatus == 1}">
<a th:href="@{|/download/${requstFile2Name}|}" th:text="${requstFile2Name}"></a>
</div>
</td>
</tr>
<th>アップロード</th>
<td>
<div class="upload-area">
<input type="file" id="fileUpload" multiple class="file-input"/>
<label for="fileUpload" class="custom-button">ファイルを選択</label>
<ul id="fileList" the file-list></ul>
</div>
</td>
</tr>
</table>
<div class="button-container">
<button onclick="submitFiles()">確定</button>
</div>
<!-- 新增结果表格 -->
<table>
<tr>
<th>結果</th> <!-- 表头 -->
<td th:each="file : ${resultFiles}">
<a th:if="${file != null}" th:href="@{|/download/${file.fileName}|}" th:text="${file.fileName}"></a>
</td>
</tr>
</table>
<!-- 履歴表格 -->
<table>
<tr>
<th class="history-header" rowspan="11">履歴</th>
<th class="year-header">年度</th>
<th class="file-name-header">文件名</th>
</tr>
<th:block th:each="year, stat : ${pastYears}">
<tr>
<td class="year-header" th:text="${year}"></td>
<td class="file-name-cell">
<!-- 仅在列表存在且有足够元素时尝试访问 -->
<th:block th:if="${histories.size() > stat.index}">
<div th:each="file : ${histories[stat.index]}">
<a th:if="${file != null}" th:href="@{|/download/${file.fileName}|}" th:text="${file.fileName}"></a>
</div>
</th:block>
</td>
</tr>
</th:block>
</table>
</div>
<script>
document.getElementById('fileUpload').addEventListener('change', uploadFiles);
function uploadFiles() {
const input = document.getElementById('fileUpload');
const fileList = document.getElementById('fileList');
fileList.innerHTML = ''; // Clear existing list
Array.from(input.files).forEach((file, index) => {
const li = document.createElement('li');
li.textContent = file.name;
li.classList.add('file-item');
const deleteBtn = document.createElement('button');
deleteBtn.textContent = '削除';
deleteBtn.className = 'delete-btn';
deleteBtn.onclick = function() { this.parentElement.remove(); };
li.appendChild(deleteBtn);
fileList.appendChild(li);
});
}
function submitFiles() {
const files = document.getElementById('fileUpload').files;
const formData = new FormData();
for (let i = 0; i < files.length; i++) {
formData.append('files', files[i]);
}
fetch('/upload', { method: 'POST', body: formData })
.then(response => response.json())
.then(data => console.log('Success:', data))
.catch((error) => console.error('Error:', error));
}
</script>
</body>
</html>

## Back-end
AdjustmentController.java
AdjustmentService.java
AdjustmentDetail.java
AdjustmentFile.java
AdjustmentRequest.java
AdjustmentDetailMapper.java
AdjustmentFileMapper.java
AdjustmentDetailMapper.xml
AdjustmentFileMapper.xml
package com.softtech.controller;
import java.time.LocalDate;
import java.util.ArrayList;
import java.util.List;
import java.util.stream.Collectors;
import java.util.stream.IntStream;
import javax.servlet.http.HttpSession;
import org.springframework.beans.factory.annotation.Autowired;
import org.springframework.stereotype.Controller;
import org.springframework.ui.Model;
import org.springframework.web.bind.annotation.GetMapping;
import org.springframework.web.bind.annotation.PathVariable;
import org.springframework.web.bind.annotation.PostMapping;
import org.springframework.web.bind.annotation.RequestParam;
import org.springframework.web.bind.annotation.ResponseBody;
import org.springframework.web.multipart.MultipartFile;
import org.springframework.web.servlet.mvc.support.RedirectAttributes;
import com.softtech.entity.AdjustmentFile;
import com.softtech.service.AdjustmentService;
/**
* 调整控制器，管理年终调整页面的请求。
*/
@Controller
public class AdjustmentController {
@Autowired
private AdjustmentService adjustmentService;
/**
* 显示年终调整页面。
* @param model Spring MVC Model
* @param session HttpSession
* @return 视图名称
*/
@GetMapping("/adjustment")
public String showAdjustmentPage(Model model, HttpSession session) {
if (session.getAttribute("userMailAdress") == null) {
return "redirect:/login";
}
int currentYear = LocalDate.now().getYear();
List<Integer> years = IntStream.rangeClosed(1, 10)
.mapToObj(i -> currentYear - i)
.collect(Collectors.toList());
String employeeId = (String) session.getAttribute("userMailAdress");
// 获取历史文件列表
List<AdjustmentFile> histories = adjustmentService.getHistoricalFiles(employeeId);
if (histories == null) {
histories = new ArrayList<>(); // 确保histories非空
}
model.addAttribute("currentYear", currentYear);
model.addAttribute("pastYears", years);
model.addAttribute("histories", histories);
return "ems/adjustment";
}
/**
* 处理文件上传请求。
* @param files 上传的文件数组
* @param session HttpSession
* @param redirectAttributes 重定向属性
* @return 重定向到成功页面
*/
@PostMapping("/upload")
public String handleFileUpload(@RequestParam("files") MultipartFile[] files, HttpSession session, RedirectAttributes redirectAttributes) {
String employeeId = (String) session.getAttribute("userMailAdress");
if (employeeId == null) {
return "redirect:/login";
}
try {
for (MultipartFile file : files) {
adjustmentService.saveFileAndDetail(file, employeeId, "type_here", LocalDate.now().getYear()); // Replace "type_here" with actual file type if needed
}
redirectAttributes.addFlashAttribute("message", "ファイルアップロード成功しました");
} catch (Exception e) {
redirectAttributes.addFlashAttribute("error", "ファイルアップロード失敗しました" + e.getMessage());
}
return "redirect:/adjustment";
}
/**
* 处理文件下载请求。
* @param filename 请求下载的文件名
* @return 文件的字节数组
*/
@GetMapping("/download/{filename}")
@ResponseBody
public byte[] downloadFile(@PathVariable String filename) {
return adjustmentService.downloadFile(filename);
}
}
package com.softtech.service;
import java.io.IOException;
import java.nio.file.Files;
import java.nio.file.Path;
import java.nio.file.Paths;
import java.nio.file.StandardCopyOption;
import java.time.LocalDate;
import java.util.ArrayList;
import java.util.Date;
import java.util.List;
import org.springframework.beans.factory.annotation.Autowired;
import org.springframework.stereotype.Service;
import org.springframework.web.multipart.MultipartFile;
import com.softtech.entity.AdjustmentDetail;
import com.softtech.entity.AdjustmentFile;
import com.softtech.mapper.AdjustmentDetailMapper;
import com.softtech.mapper.AdjustmentFileMapper;
@Service
public class AdjustmentService {
// 文件存储的基本路径
private final Path rootLocation = Paths.get("filestorage");
@Autowired
private AdjustmentFileMapper fileMapper;
@Autowired
private AdjustmentDetailMapper detailMapper;
public void saveFileAndDetail(MultipartFile file, String employeeId, String fileType, Integer fileYear) throws IOException {
String fileName = file.getOriginalFilename();
String filePath = Paths.get("uploads", employeeId, fileName).toString();
// 确保目录存在
Path destinationFile = Paths.get("uploads").resolve(Paths.get(employeeId, fileName)).normalize().toAbsolutePath();
if (!Files.exists(destinationFile.getParent())) {
Files.createDirectories(destinationFile.getParent());
}
// Save the file locally
Files.copy(file.getInputStream(), destinationFile, StandardCopyOption.REPLACE_EXISTING);
// Save file info to database
AdjustmentFile adjustmentFile = new AdjustmentFile();
adjustmentFile.setEmployeeID(employeeId);
adjustmentFile.setFileType(fileType);
adjustmentFile.setFileYear(fileYear);
adjustmentFile.setFileName(fileName);
adjustmentFile.setFilePath(destinationFile.toString());
fileMapper.insertFile(adjustmentFile);
// Example for AdjustmentDetail
AdjustmentDetail detail = new AdjustmentDetail();
detail.setYear(LocalDate.now().getYear()); // Use LocalDate to get the current year
detail.setEmployeeID(employeeId);
detail.setUploadStatus("1"); // Assuming '1' means uploaded
detail.setAdjustmentStatus("0"); // Assuming '0' means not adjusted
detail.setInsertDate(new Date());
detail.setUpdateDate(new Date());
detailMapper.insertDetail(detail);
}
/**
* 上传文件到服务器指定目录
* @param file 文件
* @param employeeId 员工ID
*/
public void uploadFile(MultipartFile file, String employeeId) {
try {
Path destinationFile = this.rootLocation.resolve(
Paths.get(employeeId)).normalize().toAbsolutePath();
if (!Files.exists(destinationFile)) {
Files.createDirectories(destinationFile);
}
file.transferTo(destinationFile.resolve(file.getOriginalFilename()));
} catch (Exception e) {
throw new RuntimeException("Failed to store file.", e);
}
}
/**
* 下载文件
* @param filename 文件名
* @return 文件的字节数组
*/
public byte[] downloadFile(String filename) {
try {
Path file = rootLocation.resolve(filename);
return Files.readAllBytes(file);
} catch (Exception e) {
throw new RuntimeException("Failed to read file.", e);
}
}
/**
* 获取指定员工的结果文件列表
* @param employeeId 员工ID
* @return 文件列表
*/
public List<String> getResultFiles(String employeeId) {
// 实现获取文件逻辑
return null;
}
/**
* 获取指定员工的历史文件列表
* @param employeeId 员工ID
* @return 历史文件列表
*/
@Autowired
private AdjustmentFileMapper adjustmentFileMapper;
public List<AdjustmentFile> getHistoricalFiles(String employeeId) {
List<AdjustmentFile> files = adjustmentFileMapper.findFilesByEmployeeId(employeeId);
if (files == null) {
return new ArrayList<AdjustmentFile>(); // 返回空列表而不是null
}
return files;
}
}
package com.softtech.entity;
import java.util.Date;
public class AdjustmentDetail {
private int year;
private String employeeID;
private String uploadStatus;
private String adjustmentStatus;
private Date insertDate;
private Date updateDate;
// Getters and Setters
public int getYear() {
return year;
}
public void setYear(int year) {
this.year = year;
}
public String getEmployeeID() {
return employeeID;
}
public void setEmployeeID(String employeeID) {
this.employeeID = employeeID;
}
public String getUploadStatus() {
return uploadStatus;
}
public void setUploadStatus(String uploadStatus) {
this.uploadStatus = uploadStatus;
}
public String getAdjustmentStatus() {
return adjustmentStatus;
}
public void setAdjustmentStatus(String adjustmentStatus) {
this.adjustmentStatus = adjustmentStatus;
}
public Date getInsertDate() {
return insertDate;
}
public void setInsertDate(Date insertDate) {
this.insertDate = insertDate;
}
public Date getUpdateDate() {
return updateDate;
}
public void setUpdateDate(Date updateDate) {
this.updateDate = updateDate;
}
}
package com.softtech.entity;
public class AdjustmentFile {
private int fileID;
private String employeeID;
private String fileType;
private int fileYear;
private String fileName;
private String filePath;
// Getters and Setters
public int getFileID() {
return fileID;
}
public void setFileID(int fileID) {
this.fileID = fileID;
}
public String getEmployeeID() {
return employeeID;
}
public void setEmployeeID(String employeeID) {
this.employeeID = employeeID;
}
public String getFileType() {
return fileType;
}
public void setFileType(String fileType) {
this.fileType = fileType;
}
public int getFileYear() {
return fileYear;
}
public void setFileYear(int fileYear) {
this.fileYear = fileYear;
}
public String getFileName() {
return fileName;
}
public void setFileName(String fileName) {
this.fileName = fileName;
}
public String getFilePath() {
return filePath;
}
public void setFilePath(String filePath) {
this.filePath = filePath;
}
}
package com.softtech.entity;
import java.util.Date;
public class AdjustmentRequest {
private int year;
private String employeeID;
private String requestFile1ID;
private String requestFile1Name;
private String requestFile1ULStatus;
private String requestFile2ID;
private String requestFile2Name;
private String requestFile2ULStatus;
private Date insertDate;
private Date updateDate;
// Getters and setters
public int getYear() {
return year;
}
public void setYear(int year) {
this.year = year;
}
public String getEmployeeID() {
return employeeID;
}
public void setEmployeeID(String employeeID) {
this.employeeID = employeeID;
}
public String getRequestFile1ID() {
return requestFile1ID;
}
public void setRequestFile1ID(String requestFile1ID) {
this.requestFile1ID = requestFile1ID;
}
public String getRequestFile1Name() {
return requestFile1Name;
}
public void setRequestFile1Name(String requestFile1Name) {
this.requestFile1Name = requestFile1Name;
}
public String getRequestFile1ULStatus() {
return requestFile1ULStatus;
}
public void setRequestFile1ULStatus(String requestFile1ULStatus) {
this.requestFile1ULStatus = requestFile1ULStatus;
}
public String getRequestFile2ID() {
return requestFile2ID;
}
public void setRequestFile2ID(String requestFile2ID) {
this.requestFile2ID = requestFile2ID;
}
public String getRequestFile2Name() {
return requestFile2Name;
}
public void setRequestFile2Name(String requestFile2Name) {
this.requestFile2Name = requestFile2Name;
}
public String getRequestFile2ULStatus() {
return requestFile2ULStatus;
}
public void setRequestFile2ULStatus(String requestFile2ULStatus) {
this.requestFile2ULStatus = requestFile2ULStatus;
}
public Date getInsertDate() {
return insertDate;
}
public void setInsertDate(Date insertDate) {
this.insertDate = insertDate;
}
public Date getUpdateDate() {
return updateDate;
}
public void setUpdateDate(Date updateDate) {
this.updateDate = updateDate;
}
}
package com.softtech.mapper;
import org.apache.ibatis.annotations.Mapper;
import com.softtech.entity.AdjustmentDetail;
@Mapper
public interface AdjustmentDetailMapper {
void insertDetail(AdjustmentDetail detail);
}
package com.softtech.mapper;
import java.util.List;
import org.apache.ibatis.annotations.Mapper;
import org.apache.ibatis.annotations.Select;
import com.softtech.entity.AdjustmentFile;
@Mapper
public interface AdjustmentFileMapper {
@Select("SELECT * FROM adjustmentfile WHERE employeeId = #{employeeId}")
List<AdjustmentFile> findFilesByEmployeeId(String employeeId);
void insertFile(AdjustmentFile file);
}
<?xml version="1.0" encoding="UTF-8" ?>
<!DOCTYPE mapper PUBLIC "-//mybatis.org//DTD Mapper 3.0//EN"
"http://mybatis.org/dtd/mybatis-3-mapper.dtd">
<mapper namespace="com.softtech.mapper.AdjustmentDetailMapper">
<!-- Insert an adjustment detail record -->
<insert id="insertDetail" parameterType="com.softtech.entity.AdjustmentDetail">
INSERT INTO adjustmentdetail (year, employeeID, uploadStatus, adjustmentStatus, insertDate, updateDate)
VALUES (#{year}, #{employeeID}, #{uploadStatus}, #{adjustmentStatus}, #{insertDate}, #{updateDate})
</insert>
<!-- Select details by employee ID -->
<select id="selectDetailsByEmployeeId" parameterType="String" resultType="com.softtech.entity.AdjustmentDetail">
SELECT * FROM adjustmentdetail WHERE employeeID = #{employeeID}
</select>
</mapper>
<?xml version="1.0" encoding="UTF-8" ?>
<!DOCTYPE mapper PUBLIC "-//mybatis.org//DTD Mapper 3.0//EN"
"http://mybatis.org/dtd/mybatis-3-mapper.dtd">
<mapper namespace="com.softtech.mapper.AdjustmentFileMapper">
<!-- Insert a file record -->
<insert id="insertFile" parameterType="com.softtech.entity.AdjustmentFile">
INSERT INTO adjustmentfile (employeeID, fileType, fileYear, fileName, filePath)
VALUES (#{employeeID}, #{fileType}, #{fileYear}, #{fileName}, #{filePath})
</insert>
<!-- Select file by ID -->
<select id="selectFileById" parameterType="int" resultType="com.softtech.entity.AdjustmentFile">
SELECT * FROM adjustmentfile WHERE fileID = #{fileID}
</select>
</mapper>